## Q2 Network Diagram
ORIGINAL:
|  | 0 | 1 | 3
|  | 1 | 2
|  | 1 | 3 | 4
[6 empty] | 4 | 4 | 10
[6 empty] | 0 | 1
[6 empty] | 4 | 6 | 10
|  | 0 | 2 | 4 | [5 empty] | 10 | 6 | 13
|  | 0 | 1 | [6 empty] | 0 | 2
|  | 0 | 4 | 4 | [5 empty] | 10 | 3 | 13
[6 empty] | 5 | 5 | 9
[6 empty] | 1 | 2
[6 empty] | 6 | 4 | 10
|  | 0 | 3 | 5 | [5 empty] | ES | ID | EF
|  | 1 | 1 | [6 empty] | SL | Resource # Required
|  | 1 | 5 | 6 | [5 empty] | LS | DUR | LF
SEE CHANGES BELOW:
Critical activites of new are 3, 5, 6.
|  | Order of scheduled activities: |  |  | The order of scheduled activities 2-1-3-4-5-6.
Recomp SL
3
2
0
2
0
0
Therefore, slack for activity 1 is 3, slack for activity 4 is 2, and slack for activity 5 is 0.
RESULTING:
| 0 | 1 | 3
| 3 | 2
| 3 | 3 | 6
[5 empty] | 4 | 4 | 10
[5 empty] | 2 | 1
[5 empty] | 6 | 6 | 12
| 0 | 2 | 4 | [5 empty] | 12 | 6 | 15
| 2 | 1 | [6 empty] | 0 | 2
| 2 | 4 | 6 | [5 empty] | 12 | 3 | 15
[5 empty] | 8 | 5 | 12
[5 empty] | 0 | 2
[5 empty] | 8 | 4 | 12
| 3 | 3 | 8 | [5 empty] | ES | ID | EF
| 0 | 1 | [6 empty] | SL | Resource # Required
| 3 | 5 | 8 | [5 empty] | LS | DUR | LF

## Q2 Time constrained schedule
Scheduled Resource Load Chart with ES and Slack updates
ID | RES | DUR | ES | LF | SL | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
1 | 2 | 3 | 0 | 4 | 1 | 0: 2; 1: 2; 2: 2
2 | 1 | 4 | 0 | 4 | 0 | bar: 0 to 3
3 | 1 | 5 | 3 | 8 | -2 | bar: 0 to 7
4 | 1 | 6 | 4 | 10 | 0 | bar: 4 to 9
5 | 2 | 4 | 8 | 12 | -2 | 5: X; 6: X; 7: X; 8: 2; 9: 2; 10: 2; 11: 2
6 | 2 | 3 | 12 | 15 | -2 | 10: X; 11: X; 12: 2; 13: 2; 14: 2
Resources Scheduled | [5 empty] | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 2 | 2 | 2 | 2 | 2
Resources Available | [5 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
LOG:
Activity Schedule: 2, 1, 3, 4, 5, 6.