## Q1 Table
Activity | Crash Cost (slope) | Maximum Crash Time | Normal Time | Normal cost
A |  | 0 | 2 | 100
B | 100 | 1 | 3 | 200
C | 40 | 1 | 5 | 200
D | 60 | 2 | 3 | 200
E | 20 | 1 | 5 | 200
F | 40 | 1 | 4 | 150
G | 0 | 0 | 2 | 150

## Q1 Network Diagram
|  |  |  | B |  | D
|  |  |  | 3 |  | 3
Cannery Hotel and Casino, Las Vegas, NV
|  | A |  |  |  | E |  | G
|  | 2x |  |  |  | 5 |  | 2x
total direct cost = 1,200
|  |  |  | C |  | F |  |  |  | project duration = 14 units
|  |  |  | 5 |  | 4 |  |  |  | the indirect cost is given as 700, so 1,900 total
Cannery Hotel and Casino, Las Vegas, NV
| A |  | B |  | D |  | G
| 2 |  | 3 |  | 3 |  | 2 |  | 10 |  | 14 time units
direct cost = 1,200
| A |  | C |  | E |  | I |  |  |  | indirect cost = 700
| 2 |  | 5 |  | 5 |  | 2 |  | 14
total = 1,900
3 paths; ABDG, ACEI, and ACFI.
| A |  | C |  | F |  | I |  |  |  | So total is $1,900
| 2 |  | 5 |  | 4 |  | 2 |  | 13 |  | The ACFI is almost critical at 13
Cannery Hotel and Casino, Las Vegas, NV
| A |  | B |  | D |  | G
| 2 |  | 3 |  | 3 |  | 2 |  | 10 |  | 13 time units
direct cost = 1,220
| A |  | C |  | E |  | I |  |  |  | indrect cost = 650
| 2 |  | 5 |  | 4 |  | 2 |  | 13
total = 1,870
REDUCE E by 1 unit (20)
| A |  | C |  | F |  | I |  |  |  | ACFI path becomes critical
| 2 |  | 5 |  | 4 |  | 2 |  | 13 |  | This makes the time units drop from 14 to 13
Direct cost becomes 1,220, but indirect cost drops from 700 to 650, so total is $1,870
Cannery Hotel and Casino, Las Vegas, NV
| A |  | B |  | D |  | G
| 2 |  | 3 |  | 3 |  | 2 |  | 10 |  | 12 time units
direct cost = 1,260
| A |  | C |  | E |  | I |  |  |  | indirect cost = 600
| 2 |  | 4 |  | 4 |  | 2 |  | 12
total cost = 1,860
REDUCE C by 1 unit (40)
| A |  | C |  | F |  | I |  |  |  | This makes the time units drop from 13 to 12
| 2 |  | 4 |  | 4 |  | 2 |  | 12 |  | Direct cost becomes 1,260, but indirect cost drops from 650 to 600, so total is $1,860
Cannery Hotel and Casino, Las Vegas, NV
| A |  | B |  | D |  | G
| 2 |  | 3 |  | 3 |  | 2 |  | 10 |  | 11 time units
direct cost = 1,320
| A |  | C |  | E |  | I |  |  |  | indirect cost = 550
| 2 |  | 4 |  | 3 |  | 2 |  | 11
total cost = 1,870
| A |  | C |  | F |  | I |  |  |  | REDUCE E again by 1 unit (40)
| 2 |  | 4 |  | 3 |  | 2 |  | 11 |  | This makes the time units drop from 12 to 11
Direct cost becomes 1,320, but indirect cost drops from 600 to to 550, so total is $1,870
This total is greater than for 12 time units, which proves the optimal number of time periods
is 12.
Due to this last network diagram, it is concluded that the 12 cost-time is the optimal one for the project, as 11 time units results in an increase in cost.
The ideal number of time units is therefore, 12. The total cost for this time schedule is $1,860.

## Q2 Network Diagram
E
Develop Input Screens
6
C
Design I/Q
4
F
A | B |  | Build Output Reports | H |  | I
Problem Definition | System Analysis |  | 4 | Test System |  | Implement System
2 | 3 |  |  | 2 |  | 3
|  | D | G
|  | Design Database | Create Database
|  | 10 | 5
[5 empty] | ES | ID | EF
[5 empty] | SL | Description
[5 empty] | LS | DUR | LF

## Q2 Gantt
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Problem Definition |  |  | Brian (pioneer)
System Analysis | [5 empty] | Ryan (development)
Design I/Q | [9 empty] | Carl (Design)
Design Database | [15 empty] | David (Data management)
Develop Input Screens | [15 empty] | Derek (Development)
Develop Output Reports | [13 empty] | Laura (Development)
Create Database | [20 empty] | Isaac (Data Analysis)
Test System | [22 empty] | Caroline (testing)
Implement System | [25 empty] | Chris (deployment)