## Q1 network
|  |  | 4 | 2 | 12 |  |  |  | 14 | 7 | 18
|  |  | 2 |  | 2 |  |  |  | 0 |  | 0
|  |  | 6 | 8 | 14 |  |  |  | 14 | 4 | 18
0 | 1 | 4 | 4 | 3 | 10 | 10 | 5 | 14 |  |  |  | 18 | 8 | 22
0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 |  | 0
0 | 4 | 4 | 4 | 6 | 10 | 10 | 4 | 14 |  |  |  | 18 | 4 | 22
|  |  | 4 | 4 | 8 | 8 | 6 | 16
|  |  | 2 |  | 2 | 2 |  | 2
|  |  | 6 | 4 | 10 | 10 | 8 | 18
[9 empty] | ES | ID | EF
[9 empty] | LS | DUR | LF

## Q1 PV plan
Schedule Information | [5 empty] | Baseline PV ($00)
Activity / Work Package | Duration | Earliest Start | Latest Finish | Slack | Total Planned Value ($00) | Planned Value up to the end of the Time period below
[6 empty] | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22
1 | 4 | 0 | 4 | 0 | 8 | Planned Value up to the end of the Time period below 2: 4; Planned Value up to the end of the Time period below 4: 4
2 | 8 | 4 | 14 | 2 | 40 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 10; Planned Value up to the end of the Time period below 10: 10; Planned Value up to the end of the Time period below 12: 10
3 | 6 | 4 | 10 | 0 | 30 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 15; Planned Value up to the end of the Time period below 10: 5
4 | 4 | 4 | 10 | 2 | 20 | Planned Value up to the end of the Time period below 6: 10; Planned Value up to the end of the Time period below 8: 10
5 | 4 | 10 | 14 | 0 | 40 | Planned Value up to the end of the Time period below 12: 20; Planned Value up to the end of the Time period below 14: 20
6 | 8 | 8 | 18 | 2 | 60 | Planned Value up to the end of the Time period below 10: 20; Planned Value up to the end of the Time period below 12: 20; Planned Value up to the end of the Time period below 14: 10; Planned Value up to the end of the Time period below 16: 10
7 | 4 | 14 | 18 | 0 | 20 | Planned Value up to the end of the Time period below 16: 10; Planned Value up to the end of the Time period below 18: 10
8 | 4 | 18 | 22 | 0 | 30 | Planned Value up to the end of the Time period below 20: 20; Planned Value up to the end of the Time period below 22: 10
Total PV by period | [5 empty] | 4 | 4 | 30 | 35 | 35 | 50 | 30 | 20 | 10 | 20 | 10
Cummulative PV by period | [5 empty] | 4 | 8 | 38 | 73 | 108 | 158 | 188 | 208 | 218 | 238 | 248

## Q1 status report
Status Report: Ending Period 2
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 50 | 4 | 4 | 4 | 0 | 0 | 1 | 1
Cumulative totals |  | 4 | 4 | 4 | 0 | 0 | 1 | 1
Status Report: Ending Period 4
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
Cumulative totals |  | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
Status Report: Ending Period 6
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
2 | 25 | 10 | 15 | 10 | -5 | 0 | 0.667 | 1
3 | 33 | 9.9 | 12 | 10 | -2.1 | -0.1 | 0.825 | 0.99
4 | 0 | 0 | 0 | 10 | 0 | -10 | 0 | 0
Cumulative totals |  | 27.9 | 37 | 38 | -9.1 | -10.1 | 2.292 | 2.99
Status Report: Ending Period 8
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
2 | 30 | 12 | 20 | 20 | -8 | -8 | 0.6 | 0.6
3 | 60 | 18 | 25 | 25 | -7 | -7 | 0.72 | 0.72
4 | 0 | 0 | 0 | 20 | 0 | -20 | 0 | 0
Cumulative totals |  | 38 | 55 | 73 | -17 | -35 | 2.12 | 2.32
Status Report: Ending Period 10
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
2 | 60 | 24 | 30 | 30 | -6 | -6 | 0.8 | 0.8
3 | 100 | 30 | 40 | 30 | -10 | 0 | 0.75 | 1
4 | 50 | 10 | 20 | 20 | -10 | -10 | 0.5 | 0.5
5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | 30 | 18 | 24 | 20 | -6 | -2 | 0.75 | 0.9
Cumulative totals |  | 90 | 124 | 108 | -34 | -18 | 3.6 | 4.2
Status Report: Ending Period 12
Task | % Complete | EV | AC | PV | CV | SV | CPI | SPI
1 | 100 | 8 | 10 | 8 | -2 | 0 | 0.8 | 1
2 | 100 | 40 | 50 | 40 | -10 | 0 | 0.8 | 1
3 | 100 | 30 | 40 | 30 | -10 | 0 | 0.75 | 1
4 | 100 | 20 | 40 | 20 | -20 | 0 | 0.5 | 1
5 | 50 | 20 | 30 | 20 | -10 | 0 | 0.667 | 1
6 | 50 | 30 | 40 | 40 | -10 | -10 | 0.75 | 0.75
Cumulative totals |  | 148 | 210 | 158 | -62 | -10 | 4.267 | 5.75

## Q1 indices table
Period | SPI | CPI | PCIB
2 | 1 | 1 | 1.61% | SPI = EV/PV
4 | 1 | 0.8 | 3.23% | CPI = EV/AC
6 | 0.73 | 0.75 | 11.25% | PCIB = EV/BAC
8 | 0.52 | 0.69 | 15.32%
10 | 0.83 | 0.73 | 36.29%
12 | 0.94 | 0.7 | 59.68%

## Q1 summary graph
Period | 2 | 4 | 6 | 8 | 10 | 12 | 14 | 16 | 18 | 20 | 22
($00) PV | 4 | 8 | 38 | 73 | 108 | 158 | 188 | 208 | 218 | 238 | 248
AC | 4 | 10 | 37 | 55 | 124 | 210
EV | 4 | 8 | 27.9 | 38 | 90 | 148
SPI | 1 | 1 | 0.73 | 0.52 | 0.83 | 0.94
CPI | 1 | 0.8 | 0.75 | 0.69 | 0.73 | 0.7
PCIB | 1.61% | 3.23% | 11.25% | 15.32% | 36.29% | 59.68%
The final results of the SPI after period 12 yielded a value
of 0.94 and the CPI after period 12 yielding a value of
0.7. If these values were over the value of 1, this project
would be running well. However, as it stands in this case
the values are below 1, meaning that the project is tracking
over budget and/or tracking late. Thus, the 2 words are late
and over budget.

## Q2
Activity | Preceding activity | Best A | Likely M | Worst B | Time est. (days) | St. Devation | Variance | Critial P Time | CP Time round | Critial P Var
a. rough in the walls | - | 11 | 12 | 13 | 12 | 0.33 | 0.11 | 12 | 12 | 0.11
b. build the bar | a | 4 | 6 | 11 | 6.5 | 1.17 | 1.37
c. run HVAC | - | 12 | 15 | 30 | 17 | 3 | 9
d. rough in electrical | b,c | 12 | 15 | 20 | 15.33 | 1.33 | 1.77
e. complete flooring | a | 7 | 12 | 22 | 12.83 | 2.5 | 6.25 | 12.83 | 12.9 | 6.25
f. get licenses | e | 2 | 17 | 19 | 14.83 | 2.83 | 8.01 | 14.83 | 14.9 | 8.01
g. install fire alarm | c,d,e | 13 | 17 | 19 | 16.67 | 1 | 1
h. deliver kitchen equip | e,f | 9 | 14 | 19 | 14 | 1.67 | 2.79 | 14 | 14 | 2.79
i. exposed ceiling reviews | c,g | 11 | 13 | 20 | 13.83 | 1.5 | 2.25
j. build stage | g,h | 12 | 13 | 16 | 13.33 | 0.67 | 0.45 | 13.33 | 13.4 | 0.45
k. sound system | j,i | 9 | 13 | 23 | 14 | 2.33 | 5.43 | 14 | 14 | 5.43
Total | [7 empty] | 80.99 | 81.2 | 23.04

## Q2 network
[7 empty] | 39.66 | H | 53.66
0
[7 empty] | 39.66 | 14 | 53.66
|  |  |  | 12 | E | 24.83 | 24.83 | F | 39.66
|  |  |  | 0 |  |  | 0
0 | A | 12 |  | 12 | 12.83 | 24.83 | 24.83 | 14.83 | 39.66
0
0 | 12 | 12 | [7 empty] | 33.83 | G | 50.5 |  | 53.66 | J | 66.99
[10 empty] | 2.66 |  |  |  | 0
|  |  |  | 12 | B | 18.5 | 18.5 | D | 33.83 | 36.49 | 16.67 | 53.16 |  | 53.66 | 13.33 | 66.9
|  |  |  | 2.66 |  |  | 2.66
|  |  |  | 14.66 | 6.5 | 21.16 | 21.16 | 15.33 | 36.49
0 | C | 17 | [7 empty] | 50.5 | I | 64.33 |  |  | 66.99 | K | 80.99
4.16 | [9 empty] | 2.66 |  |  |  |  | 0
4.16 | 17 | 21.16 | [7 empty] | 53.16 | 13.83 | 66.99 |  |  | 66.99 | 14 | 80.99
[12 empty] | A: | E to H was a redundant link I removed, as seen by the X
[12 empty] | A: | C to G was a redundant link I removed, as seen by the X
[12 empty] | A: | C to I was a redundant link I removed, as seen by the X
[12 empty] | B: | AEFHJK - red arrow refers to Critial Path
[12 empty] | C: | Slack: | A = 0 | B = 3 | C = 5 | D = 3 | E = 0
[12 empty] | C: | F = 0 | G = 3 | H = 0 | I = 3 | J = 0 | K = 0
[12 empty] | D: | LEAST sensitive element: |  | C, with a slack of 5.
[12 empty] | D: | MOST sensitive element: |  | B, D, G, I with a slack of 3.
|  | early start |  |  |  | early finish | start from right for this: |  |  |  |  | E: | PROJECT DURATION (CP): |  | Te = 80.99 = 81
|  |  | ES | ID | EF |  | where | LF - DUR = LS |  |  |  | F: | Probability of meeting schedule duration: 65%
|  | float | [5 empty] | LS becomes LF of next node, unless previous node is a burst
|  |  | LS | DUR | LF |  |  | if it is a bust*, smallest LS takes the LF for that node
|  | late start |  | duration |  | late finish | [5 empty] | Z = | Z = (Ts - Te) / SQRT(Sum var te2)
[12 empty] | = | (83 - 81.2) / sqrt(23.04)
[12 empty] | = | 0.375
[12 empty] | Z = 0.38. | This means there is a 64.8% chance of being successful.
Z table at 0.38 = 0.6480
Thus, 65% probability.